Charlotte Roberts
Tel: No. 01865 541948
Date: 16 September 2022 Email: Charlie.roberts@thamesvalley.police.uk

Dear Chief Constable

##### Performance & Accountability Meeting (PAM)
You are requested to attend a PAM meeting on Thursday 22 September 2022 at 1330hrs in the CCMT meeting room and/or MS Teams for those who are unable to attend.
Microsoft Teams meeting
Join on your computer or mobile app
Click here to join the meeting
Or join by entering a meeting ID
Meeting ID: 351 913 058 915
Passcode: SctuTw
Or call in (audio only)
+44 20 7660 8499,,44911036# United Kingdom, London Phone Conference ID: 449 110 36#

Yours sincerely

Martin Thorney
CFO & Deputy Chief of Staff (Vice Chief of Staff)

Agenda Item	Page No.

1. Apologies – Martin Thornley & Linda Waters	-
2. Minutes of the PAM meeting held on 21 July 2022	3 - 6
(PCC Matthew Barber)
OPCC Strategic Delivery Plan 2021-2025	7 - 20
(Gillian Ormston)

TVP Strategic Plan 2022/23	21 - 34
(Chief Constable)

Decisions under the Scheme of Governance	35 - 39
(Chief Constable)

NOTE: For any questions in relation to the Decisions under the Scheme of Governance paper, please submit these to Linda Waters in advance of the meeting on 22 September 2022.

AOB	-

##### Date of next PAM meeting: Tuesday 29 November 2022 at 1030hrs in the CCMT Meeting Room HQ South or MS Teams
AGENDA ITEM 2
#### 3

##### POLICE & CRIME COMMISSIONER FOR THAMES VALLEY MINUTES OF THE PERFORMANCE AND ACCOUNTABILITY MEETING
HELD IN THE CCMT MEETING ROOM AND/OR VIA MS TEAMS ON 21 JULY 2022 COMMENCING AT 10:30 HRS

Present:
M Barber (Police & Crime Commissioner) (OPCC) J Campbell (Chief Constable) (TVP)
L Waters (Director of Finance) (TVP)
I Thompson (Chief Finance Officer & Deputy Chief Executive) (OPCC)
C Widdison (Corporate Governance Officer, Strategic Governance Unit) (TVP) J Weems (Chief Supt. Force Intelligence & Specialist Operations) (TVP)
S Bosley (Det. Supt. CID Command) (TVP)
M Butler (Lead Advisor, Service Improvement) (TVP)
G Evans (Policy Development Officer, Policing & Performance) (OPCC) C Roberts (Executive Assistant to the PCC) - Minutes (OPCC)

##### Apologies:
J Hogg (Deputy Chief Constable) (TVP)
J Kidman (Chief Supt. Head of Governance & Service Improvement) (TVP)

Agenda Item

Apologies

The Police & Crime Commissioner (PCC) welcomed attendees to the meeting.

Minutes of the PAM meeting held on 30 May 2022

The (PCC) went through the minutes of the meeting from 30 May confirming they were accurate.

Andrew Grimley (AG) had been liaising with Paul Hammond (PH) who had now left the OPCC to discuss major force projects and provide an update to the (PCC). Claire Widdison (CW) confirmed this was still ongoing and would link in with (AG) and also Ian Thompson (IT).

Action: Claire Widdison (CW) would obtain an update on major force projects and ask (AG) to link in with Ian Thompson (IT) to provide an update.

The Chief Constable (JC) would provide an update on physical response times and additional data to the (PCC) during the TVP Strategic Plan.

1

PEEL AFI’s update

(CW) had been informed TVP would be subject to a thematic inspection in September 2022 around CSE and also an Firearms Policing inspection, although (CW) was still awaiting a date for this possibly around December 2022. If there were any significant concerns, the Force would provide an update to the (PCC). Chief Supt. Jim Weems (JW) provided additional information on NCA and law enforcement and international crimes but more work was still required as currently only receiving an IP address and GEO location to go from. Thames Valley has a higher footprint compared to other forces.

(CW) attended a recent meeting around CDI where a national decision would be taken later in the year. The PCC noted that (JC) and (PCC) to discuss further strategies around the inspections especially around hate crime.

There was good progress made on ‘use of force’. The PCC NOTED the PEEL AFI update.
Treasury Management Quarterly Performance Update

(IT) provided a summary on the economy noting that CPI inflation had risen to 9.4% but is expected to increase further to circa 11% in the coming months. Base rate is currently at 1.25% but increase by 0.5% next time. The OPCC have invested £43 million so far this month in fixed term deposits. IT is now forecasting £2.3 million in interest receipts this year which is £1.6m higher than the annual budget of £0.7m. There will be scope to increase the annual budget later in the year. Exceeded the overdraft limit once this year due to South Oxfordshire missing their precept payment.

The PCC NOTED the Treasury Management Quarterly Performance Update

OPCC Strategic Delivery Plan 2021-2025

The OPCC Strategic Delivery Plan would be discussed at next week’s Senior management Group meeting.

TVP Strategic Plan 2022/23

(JC) summarised crime overview and noted Thames Valley were 10th out of 43 nationally in crime prevention, reducing levels of neighbourhood crime and antisocial behaviour.

The National Outcomes Framework was measured at a national level; the data was not broken down or available on an individual force basis.

(JC) reported on call handling and call waiting times, and had asked ACC Catherine Akehurst (CA) to put together a plan. A new Chief Supt. would be in place shortly and work was being carried out on the plan which was fairly significant. (JC) went through the average time taken to answer 101 calls/proportion of callers waiting over 10 minutes for their call to be answered. In July ,the average time recorded for Thames Valley was 9 minutes 44 seconds.

(JW) referred to the OCGs and the increased number of disruptions and successful prosecutions for serious organised crime. There had been 45 recorded OCGs across the Force and more SOC threats than OCGs. Work was being carried out to ensure OCGs were also scored consistently, i.e.
2

that investigators knew when to score and how to correctly record information non ‘AMPIS’ and what processes to follow in relation to Terminate, Treat, Transfer and Tolerate. Thames Valley had a good OCG structure in place. Primary criminality for Q1 for LPA and units in Thames Valley were also summarised.

There had been 129 arrests recorded during Q1 2022/23 with 25 of these convicted.

A Drugs Focus Taskforce had been created and an update provided as to where Thames Valley were so far. Every quarter there was a partnership briefing where 50 people dialled in from CSPs who also received this information and (JW) would also forward this information to the (PCC).

Action: (JW) to send the PCC the additional OCG slides discussed during today’s meeting

(JC) confirmed there was good compliance for ‘Op Signature’ to protect victims from suffering further losses, as scam victims were repeatedly targeted. ‘Op Signature’ demand reduced by 33% showing the highest rate of ECU1 form completion for the year. There was a 10% increase in the volume of DA cases where formal action had been taken.

Action: As to unauthorised encampments, the (PCC) noted he would like to see more detail for included in the slide for future meetings and would discuss this with (JC) this afternoon.

(JC) went through the organisational performance key indicators. The overall hours lost due to sickness for Q1 was 211,140. This was a decrease from Q4 in 2021/22 and was going still in the right direction. There was also psychological sickness included in the figures and (CW) wished the (PCC) to be aware of this.

The PCC NOTED the TVP Strategic Plan and OCG update.

Decisions under the Scheme of Governance

Linda Waters (LW) provided a short brief update on decisions taken under delegated powers. The PCC NOTED the Decisions under the Scheme of Governance.
Update on OCG’s

Chief Supt. Jim Weems (JW) provided an update on OCGs during agenda item 6.

RASO charge rates, progress and ongoing challenges

Det. Supt. Stuart Bosley (SB) referred to the slides and outcome rates which were up set out on page 46 and 47 in the agenda and which showed an increase of 17%. Reporting levels were slightly down in rape reporting and this put Thames Valley 19th place in the country although there was still more work to be done. The RASO role had been expanded and recruitment had been fulfilled. (SB) had also been working with Candy Heinrich (CH) and Helen Wake (HW) from the OPCC.

A crime management process had been put in place around RASO to reinforce standards and these were now being managed properly. (SB) would be carrying out six monthly reviews to focus on where the Force needed to be. There was a good working relationship with the CPS and they were looking to expand to ISVA.

3

As to the Witness Care Units, there was a dedicated RASO caseworker dealing with approximately 60 cases. (SB) had applied for VAWG funding to enable another post for additional staff and awaited the outcome of the bid. The (PCC) asked (SB) what proportion were new offences rather than historic offences? (SB) would need to collate the figures for the PCC if required but was trying to find strategies for prevention of rape and sexual assault. There was now a much better level of reporting. In relation to rape investigation reporting, there was an understanding of ‘consent’ but the public needed be in control and aware. The CSE proportion had seen a decline in rape offences but seen an increase in crime levels. (SB) noted the team would be involved in working with LPAs around the ‘bluestone’ principles but needed caution around this. (SB) would like to see performance rates increase for Thames Valley and there was always room for improvement.

AOB

No other business to discuss.

The meeting concluded at 12:05 hrs

##### Date of next PAM meeting: Thursday 22 September 2022 at 14:00hrs in the CCMT meeting room, HQ South or via MS Teams.

4

OFFICE OF THE POLICE & CRIME COMMISSIONER FOR THAMES VALLEY

Report for Information: PCC’s Performance and Accountability Meeting, 22nd September 2022

Title: OPCC Strategic Delivery Plan 2021-2025

Executive Summary:

The PCC’s Police and Criminal Justice Plan 2021-2025 presents a combination of policing and non-policing strategic priorities, objectives and planned activities.

The PCC’s Chief of Staff, Chief Finance Officer and other members of his Office of the PCC (OPCC) Strategic Management Group are responsible for ensuring that all non-operational policing strategic priorities and objectives within the Police and Criminal Justice Plan are monitored and delivered on a timely basis.

The key activities and actions underpinning the delivery of the PCC’s strategic priorities and objectives are captured within the OPCC’s internal ‘Strategic Delivery Plan’, and update reports are presented to the PCC on a regular basis throughout each year to enable the PCC to monitor progress on their delivery.

Attached is a copy of the OPCC Strategic Delivery Plan for 2021-2025. Appendix 1 lists all one-off projects
Appendix 2 lists all ‘Business as Usual & Cyclical’ ongoing actions.

This OPCC Strategic Delivery Plan is a ‘live’ internal management document which will be reviewed and refreshed regularly throughout each year of the Plan, providing a rolling update of progress.

For information, the Chief Constable will be held to account for delivering the long- term strategic policing priorities and objectives within the PCC’s Police and Criminal Justice Plan, and year-on-year progress will be measured against the Force’s own ‘Annual Strategic Plan’.

Recommendation:

1.	That the PCC notes progress on the delivery of the actions contained within the OPCC Strategic Delivery Plan 2021-2025.

Police and Crime Commissioner
I hereby approve the recommendation above.

Signature	Date

Page 1 of 4

PART 1 – NON-CONFIDENTIAL

Introduction and background

  1. The PCC published his four-year Police and Criminal Justice Plan 2021–2025 in June 2021.

  1. Within the Office of the PCC (OPCC), the PCC holds his Chief of Staff, Chief Finance Officer and other members of his Strategic Management Group to account for delivery of the non-operational strategic policing priorities and objectives set out within the Police and Criminal Justice Plan. This includes those service activities to be delivered by external partners and commissioned service providers, such as community safety partnerships and victims’ service providers, who receive funding from the PCC to do so.

  1. Attached is a copy of the OPCC Strategic Delivery Plan (SDP) for 2021-2025. The SDP presents key activities and ‘Actions’ underpinning the delivery of the PCC’s strategic priorities and objectives, as set out in the Police and Criminal Justice Plan, as follows:

    1. Improving the criminal justice system
    2. Fighting fraud and cybercrime
    3. Tackling illegal encampments
    4. Strong local policing
    5. Fighting serious organised crime
    6. Governance and accountability
    7. Other

  1. Appendix 1 lists all one-off projects (42) whereas Appendix 2 lists all ‘Business as Usual & Cyclical’ ongoing actions (50), comprising 92 actions in total. Appendix 3 provides an audit trail of the 22 completed one-off projects

  1. Progress on the delivery of the 92 actions contained in the attached appendices is summarised below:

Progress	Appendix 1 / (Projects)	Appendix 2 / (BAU)	Total

Completed	3	17	20
On Track	20	26	46
At Risk	0	1	1
Significant Risk	0	0	0
Not Commenced	20	7	27

Total	43	51	94

  1. For information, the PCC separately holds the Chief Constable to account for the efficient and effective performance of the Force in delivering the relevant operational ‘policing’ objectives and planned outcomes contained within the Plan.

Page 2 of 4

Issues for consideration

  1. This SDP document is used throughout each financial year covered by the SDP to inform the PCC as to the performance of the OPCC in terms of whether scheduled activities and actions are being adequately progressed, and planned outcomes are being successfully delivered.

Financial comments

  1. There are no specific financial implications arising from this report.

Legal comments

  1. There are no specific legal implications arising from this report.

Equality and Diversity comments

  1. There are no equality and diversity implications arising from this report.

Background papers
Police and Criminal Justice Plan 2021-2025

Public access to information / Information in this report is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date / would compromise the implementation of the decision being approved.
Is the publication of this form to be deferred? No
Is there a Part 2 form? No

Name & Role	Officer
Head of Unit / The annual Strategic Delivery Plan explains how the OPCC will implement and monitor delivery of the non-operational policing activities, actions and outcomes, as set out in the Police and Criminal Justice Plan 2021-2025, during 2021/22.	OPCC Chief Executive
Legal Advice / There is no statutory requirement to produce a strategic delivery plan to oversee delivery of the Police and Criminal Justice Plan.	OPCC Head of Governance & Compliance
Financial Advice / There are no financial implications arising from this report.	OPCC Chief Finance Officer
Equalities and Diversity / No issues arising from this report.	OPCC Chief Executive

Page 3 of 4

PCC STATUTORY CHIEF OFFICERS’ APPROVAL

We have been consulted about the report and confirm that appropriate financial and legal advice has been taken into account.

We are satisfied that this is an appropriate report to be submitted to the Police and Crime Commissioner.

Chief of Staff	Date 16th September 2022

Chief Finance Officer	Date 16th September 2022

Page 4 of 4

        OPCC Strategic Delivery Plan 2021-2025
PROJECT & ANNUAL ACTIONS
3	APPENDIX 1
20
Completed
On track
At risk
Significant risk
Not commenced

0
0
20
43

Business Area	Ref	Action	Strategic Priority	Start Date	Due Date	SMG Sponsor	Lead Officer	RAG	Progress
Community Safety	001	Project manage the TV Prison Leavers programme of work including: / Whole system review / Develop partnership model through RRO board / Engage with Bullingdon on prison based services / Enhance community based provision	Criminal justice	Jun-21	Jun-23	Cath Marriott	Rachel Batts	On track	Restart Team at full capacity. ISA issues resolved and starting to work with a handful of clients during Sept ahead of launching with full ICT infrastructure in place in October. There continues to be excellent partnership engagement despite significant demand on organisations such as Prisons and Probation. There has been sudden changes of personnel at Bronzefield which is being discussed presently.
Community Safety	002	Develop and publish Reducing Reoffending Strategy	Criminal justice	Dec-21	Dec-22	Matthew Barber	Cath Marriott	On track	Data gathering mostly complete from LCJB and YJB (YOTs) to add to Prison Leaver's work. Paused for handover to new LCJB programme manager. Whole Systems Review published in May 2022 which will form a large part of strategy content.
Community Safety	004	Develop and publish Cyber Crime & Fraud Prevention Strategy	Cyber & fraud	May-22	Dec-22	Matthew Barber	Cath Marriott	On track	Currently designing structure, high level content and identifying key contributors. Proposal to separate Fraud from Cyber Crime as Fraud is a significant issue on its own.
Community Safety	005	Develop and publish Illegal Encampment Strategy / - including the use of a transit site(s)	Illegal Encampments			Matthew Barber	April Smith	Not commenced
Victims	007	Develop process for sharing learning from Domestic Homicide Reviews	Other	Dec-22	Jun-23	Helen Wake	Candy Heinrich / & Wendy Walker	On track	Early scoping work has started
Community Safety	008	Community Speedwatch: / Support the roll out of CSWO to existing groups / Recruit new groups to take part in speedwatch / Provide starter kits to new groups / Ongoing support for volunteers	Local Policing	Nov-21	Mar-23	Cath Marriott	Jacob Nurdan	On track	All kits distributed. Process being drawn up for further procurement. / Nearing 1000 volunteers across 200 schemes. Scheme proving very popular. Managing expectations needed.
Community Safety	009	Drive improvements in analysis and evidence-based decision making across CSPs, through analytical capacity building, upskilling, provision of tools and support	Local Policing	May-21	Mar-23	Cath Marriott	Aaron Cheung	On track	Collaboration taking place with Oxon and all Berkshire CSPs for the OPCC to host 2 additional local analysts, enabling consistency of access to data and quality of analytical product. These are out for advert, with interviews scheduled later in Oct. OPCC analyst supporting multiple CSPs with their strategic assessment and other analysis work such as Safer Streets.

Community Safety	010	Implement a peer-assessment / health check process for CSPs to support development and peer- to-peer mentoring.	Local Policing	Jan-22	Mar-23	Cath Marriott	Cath Marriott	On track	CSP review published and shared. Wokingham / & West Berkshire reviews complete. Bracknell scheduled in Sept (2022)
Community Safety	011	Develop and publish Neighbourhood Policing Strategy	Local Policing			Matthew Barber	Cath Marriott	Not commenced
Community Safety	012	Develop and publish Road Safety Strategy	Local Policing	Feb-22	Jan-23	Matthew Barber	Cath Marriott	On track	Currently designing structure, high level content and identifying key contributors. Will be discussed at Nov Road Safety summit.
Community Safety	020	Review OPCC and Victims First websites and implement changes	OPCC / Governance	Jan-22	Nov-22	Cath Marriott	Sarah Stokes	On track	TVP Procurement and ICT have given the go ahead for us to work with Indigo Tree on the site. The implementation timeline has now been agreed and the site is set to go live by end September.
Community Safety	022	Develop and publish Serious Violence and Knife Crime Strategy	Organised Crime	Nov-21	Dec-23	Matthew Barber	Cath Marriott	On track	Supporting CSPs in their local strategies and Needs Assessments and propose that the PCC Strategy incorporates key elements that run through multiple CSPs
Community Safety	023	Implement fly-tipping reduction scheme in partnership with local authorities / - Launch pilot with West Oxfordshire District Council	Other	Jul-22	tbc	Cath Marriott	TBC	Not commenced
Community Safety	025	Develop and publish Fly-Tipping and Environmental Crime Strategy	Other			Matthew Barber	Cath Marriott	Not commenced
Governance	052	Develop and publish Mental Health Strategy	Criminal justice			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	053	Develop and publish Cyber Crime & Fraud Reporting Strategy	Cyber & fraud			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	054	Develop and publish Digital Investigations Strategy	Cyber & fraud			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	060	Develop and publish Staff/Officer Recruitment and Retention Strategy	Force Governance			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	061	Develop and publish Contact Management Strategy	Force Governance			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	062	Develop and publish Specialist Capabilities Strategy	Force Governance			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	063	Develop and publish Officer Welfare Strategy	Force Governance			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	064	Develop and publish ANPR Strategy	Force Governance			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	068	Develop and publish Rural Crime Strategy	Local Policing			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	069	Develop and publish Business Crime Strategy	Local Policing			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff

Governance	070	Develop and publish Pet Theft Strategy	Local Policing			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	087	Develop and publish Emergency Services Collaboration Strategy	OPCC / Governance			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Victims	089	Develop and publish Sexual Exploitation and Child Abuse Strategy	Organised Crime			Helen Wake	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	090	Develop and publish Serious Organised Acquisitive Crime Strategy	Organised Crime			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Governance	091	Develop and publish Tackling Illegal Drugs Strategy	Organised Crime			Matthew Barber	Gillian Ormston	Not commenced	Purpose, Scope and Timetable still to be determined. Will be picked up by the New Chief of Staff
Victims	093	Develop partnership governance structure of Rape / & Sexual Assault (RASA) service landscape	Criminal justice	Sep-22	Mar-23	Helen Wake	Candy Heinrich	On track	New TVP RASO team in now in place that has reignited current partnership structures. Regular meetings are held between OPCC and TVP. Currently considering Strategic Board but first need to engage with appropriate mental health commissioners.
Victims	094	Review complex needs and domestic abuse (DA) provision	Criminal justice	Aug-21	May-22	Helen Wake	Candy Heinrich	Completed	Funding has been agreed for a further 12 months for the complex needs services. / Further consideration in regards to longer term complex needs provision have been covered as part of the recent Review of Victims Services and will now be covered in future the commissioning strategy.
Victims	095	Develop and publish Support for Victims in Criminal Justice Strategy including: / The Victims Law / Victims Code of Practice (VCoP) compliance framework	Criminal justice	Dec-21	Mar-23	Helen Wake	Candy Heinrich	On track	Victims Law consultation has recently concluded. The Outcomes from the consultation will and are being used to inform service provision and practice.
Victims	096	Develop and publish Support for Victims outside of Criminal Justice Strategy	Criminal justice	Dec-21	Oct-23	Helen Wake	Wendy Walker	Not commenced
Victims	097	Develop and publish Domestic Abuse Strategy	Criminal justice		Oct-22	Helen Wake	Candy Heinrich	On track	A Safety of Women and Girls Strategy which covers DA has been completed in draft form and will be published shortly.
Victims	098	Develop and publish 'Rape and Sexual Offending' (RASO) Strategy	Criminal justice		Oct-22	Helen Wake	Candy Heinrich	On track	A Safety of Women and Girls Strategy which covers RASO has been completed in draft form and will be published shortly.
Victims	100	Provide quarterly and standardised victim services framework data to promote the work and outcomes associated with Victims First via the Victims First website.	Criminal justice	Dec-21	Ongoing	Helen Wake	Wendy Walker / Sarah Stokes	On track	New performance measures have been developed for all core victims services
Victims	102	Visit all VF delivery providers and conduct one annual themed audit of part of their services to inform action plans for service improvement.	Criminal justice	Dec-21	Mar-22	Helen Wake	Wendy Walker	Completed	Findings from the audit fed into the Victims Service Review
Victims	103	To attract, recruit and retain appropriate counsellors into the counselling service by improving recruitment processes / (e.g. JD, interview process, treatment room audit, etc.)	Criminal justice	Dec-21	Ongoing	Helen Wake	Candy Heinrich	On track	We have been successful in obtaining additional funding to provide qualified screening post who will take over recruitment of new counsellors and complete a full review if the service.

Victims	104	To improve quality standards of interventions offered by the counselling service and reduce attrition rate: / Improve therapeutic trauma provision for children / Improve evidence-based therapeutic interventions for adults / review access into service and implement an assessment process	Criminal justice	Oct-21	Oct-22	Helen Wake	Candy Heinrich	On track	We have been successful in obtaining additional funding to provide qualified screening post who will take over recruitment of new counsellors and complete a full review if the service.
Victims	105	Improve referral pathways between Victims First Services and mental health providers and services.	Criminal justice	Dec-22	Dec-22	Helen Wake	Candy Heinrich	On track	Meeting are being set with appropriate mental health commissioners
Victims	111	Explore options for developing a victims’ needs assessment, and implement preferred option, to provide evidence base to support future commissioning decisions.	Criminal justice	Nov-21	May-22	Helen Wake	Wendy Walker	Completed	Previous needs assessments have been reviewed and have been updated
Victims	106	Develop a range of mechanisms to incorporate the voice of the victim in victim service provision	Criminal justice	Aug-22	Dec-22	Helen Wake	Candy Heinrich	On track	Engagement with victims has already taken place via a range of surveys and the first Victims Voice Forum is due to take place in October.
Victims	107	Recommissioning of new victim service provision	Criminal justice	Aug-22	Mar-24	Helen Wake	Candy Heinrich and Wendy Walker	On track	The review of current victim provision has informed the starting point for recommissioning. Demand Mapping currently taking place and co production events with providers booked for November.

        OPCC Strategic Delivery Plan 2021-2025
'BUSINESS AS USUAL' & CYCLICAL ACTIONS
17	APPENDIX 2
26
Completed
On track
At risk
Significant risk
Not commenced

1
0
7
51

Business Area	Ref.	Action	Strategic Priority	Start Date	Due Date	SMG Sponsor	Lead Officer	RAG	Progress
Community Safety	015	Review Community Safety Fund grant allocations and implement changes ahead of the next financial year.	OPCC Governance	May-22	Dec-22	Cath Marriott	Cath Marriott	Completed	Changes complete and implemented. Reviewing CSP experience of new process prior to closing this action
Community Safety	016	Manage the existing Community Safety Fund that is granted to CSPs through regular monitoring and scrutiny	OPCC Governance	May-22	Mar-23	Cath Marriott	Cath Marriott	On track	To reduce unnecessary demand on CSPs, first monitoring will be no earlier than October 2022
Community Safety	017	Ensure auditable due diligence and proportionate regular monitoring of CSF grants to external organisations through grant and service level agreements	OPCC Governance	May-22	Apr-23	Cath Marriott	Cath Marriott	On track	Expecting a formal audit of CSF processes in Q3 of financial year 2022/23
Community Safety	018	Develop forward commissioning options for the deployment of non-CSP Community Safety Fund monies, aligned to the P&CJ Plan	OPCC Governance	Jun-22	Dec-22	Cath Marriott	Cath Marriott	On track	Collating partnership information on existing investment / / activity to identify gaps which would benefit from CSF funding consideration.

Community Safety	019	Implement a new OPCC Communications Strategy	OPCC Governance	May-22	Apr-23	Cath Marriott	Heather Sherkunov	On track	Ongoing development of the overarching Communications Strategy – continually updated and being delivered.
Community Safety	021	Continue to support the work of the Violence Reduction Unit	Organised Crime	May-21	May-23	Matthew Barber	Cath Marriott	On track	Monthly touchdown meetings taking place. Supporting their Nov VCS event
Community Safety	024	Seek business cooperation and sponsorship opportunities	Other	Nov-21	Apr-23	Cath Marriott	Cath Marriott	On track	No new updates
Finance	026	Strategic review of all OPCC draft budgets for 2023/24, including Ministry of Justice (MoJ) grant funding, to ensure the most effective use of resources.	Criminal justice	Oct-22	Nov-22	Martin Thornley	Martin Thornley	Not commenced
Finance	027	Review Force and OPCC budgets including ongoing review of police officer and staff numbers	Force Governance	Oct-22	Ongoing	Martin Thornley	Martin Thornley	Not commenced
Finance	028	Work with TVP Corporate Finance to prepare and publish the 3 year medium term financial plan (MTFP) 2023/24 to 2025/26.	Force Governance	Sep-22	Feb-23	Martin Thornley	Martin Thornley	Not commenced
Finance	030	Manage corporate property matters through Strategic Estates Group and work to deliver a future estates strategy	Force Governance	May-21	Ongoing	Matthew Barber	Martin Thornley	On track
Finance	034	Close the 2021/22 accounts in accordance with best practice and submit to Ernst & Young external auditors (EY) by 30 May 2022.	OPCC Governance	Apr-22	Jun-21	Martin Thornley	Rachael Martinig	Completed	Accounts closed and draft Statement of Accounts submitted for audit before 31 May 2022
Finance	035	Liaise with external audit and then present the audited accounts to the Joint Independent Audit Committee (JIAC) prior to publication on the PCC’s website.	OPCC Governance	Jun-22	Sep-22	Martin Thornley	Rachael Martinig	On track	Audit in final stages awaiting assurance from Bucks pension fund.
Finance	036	Complete the 2020/21 and 2021/22 ‘Whole of Government Accounts’ (WGA) return and submit to HM Treasury.	OPCC Governance	Apr-22	Dec-22	Martin Thornley	Rachael Martinig	On track	2021/22 Return not yet available (expected Autumn 2022). Cycle 1 submitted for 2020/21.
Finance	037	Update specific OPCC controlled budget allocations (e.g. OPCC, capital financing) and ensure they are reflected in the updated 2023/24-2025/26 Medium Term Financial Plan (MTFP).	OPCC Governance	Oct-22	Nov-22	Martin Thornley	Rachael Martinig	Not commenced
Finance	038	Complete and submit all statutory returns and Government grant returns in accordance with required timescales.	OPCC Governance	Apr-22	Mar-23	Martin Thornley	Rachael Martinig	On track

Finance	039	Undertake the VAT partial exemption calculation for 2022/23.	OPCC Governance	May-22	Mar-23	Martin Thornley	Rachael Martinig	Not commenced
Finance	040	Work with external advisors to explore VAT opportunities as appropriate.	OPCC Governance	May-22	Mar-23	Martin Thornley	Rachael Martinig	Not commenced	Withdrawn from the Royal Mail claim
Finance	041	Ensure all treasury management activity is conducted in accordance with agreed treasury management strategy.	OPCC Governance	Apr-22	Mar-23	Martin Thornley	Rachael Martinig	On track
Finance	044	Prepare for new financial reporting standard IFRS 16 on 'Leasing'. Set up project group to identify all leases captured by the standard that will be brought onto the balance sheet and prepare all appropriate lease calculations and accounting entries	OPCC Governance	May-22	Mar-24	Martin Thornley	Rachael Martinig	On track	IFRS 16 has been deferred for 2 years. New implementation date is April 2024
Finance	045	Produce and present the 2021/22 Internal Audit Annual Report to the Joint Independent Audit Committee (JIAC) meeting in June 2022.	OPCC Governance	Jun-22	Jun-22	Martin Thornley	Neil Shovell	Completed	Report submitted to and endorsed by the JIAC at its meeting on 17 Jun 2022.
Finance	046	Produce regular JIAC update reports on: / Progress of 2022/23 Internal Audit Plan delivery and summary of matters arising from completed audits; and / Progress of delivery of agreed actions in internal audit reports.	OPCC Governance	May-22	Mar-23	Martin Thornley	Neil Shovell	On track	Progress update reports to be issued to the 17 Jun, 7 Oct and 16 Dec 2022 and 17 Mar 2023 JIAC meetings.
Finance	048	Implement the Internal Audit team’s Quality Assurance and Improvement Programme (QAIP) Action Plan. / This will include any areas raised as part of the team’s External PSIAS Assessment and recommendations from the recent CIPFA Internal Audit: Untapped Potential national review.	OPCC Governance	May-22	Mar-23	Martin Thornley	Neil Shovell	On track	The team’s QAIP was developed for 2022/23 and has been implemented. Updates have been provided to the JIAC and Internal Audit Oversight Group. / The outcome of the team's External PSIAS Assessment was received in Jun 2022, which will be reported to the JIAC and Internal Audit Oversight Group. Actions to be noted in the QAIP. / The CIPFA Internal Audit: Untapped Potential report has been reviewed. No actions needed to be include within the QAIP.
Governance	055	Establish a framework for monitoring Force performance against the Police & Criminal Justice Plan	Force Governance	Jul-21	Ongoing	Gillian Ormston	Gary Evans	Completed	TVP 2021/22 performance report submitted to PAM in Nov 2021, Jan & Mar 2022 (links to Ref 067)
Governance	056	Establish monitoring system and ensure responses to HMICFRS inspections	Force Governance	Aug-21	Ongoing	Gillian Ormston	Gary Evans	Completed	GE now attending Force Improvement & Innovation meetings to monitor wider implementation of HMICFRS recommendations. Imminent release of the PEEL inspection report will require an update to the Force recommendations spreadsheet, before being shared with the PCC.
Governance	057	Establish complaints handling monitoring system and ensure responses to IOPC recommendations	Force Governance	Aug-21	Ongoing	Vicki Waskett	Sierra Reid	Completed	Liaison with IOPC Oversight Officer in order to confirm that the OPCC receive all IOPC recommendations, and system put in place to record recommendations and monitor their implementation by the Force and OPCC. IOPC complaints data now published on PCC's website together with accompanying narrative (linked to reference 067).
Governance	059	Operate an efficient and effective Independent Custody Visiting Scheme	Force Governance	May-21	Ongoing	Vicki Waskett	Jim Katouzian	Completed	Service currently 'business as usual' incorporating appropriate Covid pandemic health & safety risk mitigation arrangements.

Governance	065	Major Force projects - review of existing governance arrangements and develop new governance framework for PCC oversight and scrutiny of major Force projects	Force Governance	Sep-21	Mar-22	Matthew Barber	Gillian Ormston	On track	Internal Audit brief agreed with NS. A Grimley (AG) to act as TVP liaison point. Proposed new Major Project Governance framework presented to and endorsed by Police / & Crime Panel on 8 Apr 2022. Next stage (in conjunction with AG) - TVP to develop project management performance / & progress reporting templates and implement framework.
Governance	066	Ensure the OPCC complies with additional or changed responsibilities regarding police complaints system resulting from the Policing and Crime Act 2017 reforms.	Force Governance	May-21	Ongoing	Vicki Waskett	Sierra Reid	Completed	New Complaints Review Manager in post and backlog of reviews has reduced by apx. 70%.
Governance	067	Ensure compliance with reporting to Home Office regarding 'National Crime & Policing Measures' and compliance with the Government's 'Beating Crime Plan'	Force Governance	May-21	Ongoing	Gillian Ormston	Gary Evans	At risk	The Elected Local Policing Bodies (Specified Information) (Amendment) Order 2021: guidance for police and crime commissioners - GOV.UK (www.gov.uk) / The PCC is compliant with the Specified Information Order Regulations relating to the Crime & Policing Measures, as far as possible using the available published data. Internally, the Force continues to use proxy measures although these are modified when published for the PCC’s PAM meeting. The OPCC is monitoring the national measures via the Home Office ‘Digital Crime and Performance Pack’, although this information cannot at present be reproduced in the public domain. We continue to work closely with APACE and APCC to identify good practices in developing a PCC Statement. When resources allow the Force intend to replicate the model used in Avon & Somerset in order to better present this information. The PCC is compliant with the other performance elements of the SIO – i.e. publishing the most recent PEEL report and IOPC complaints data.
Governance	071	Support for the Special Constabulary: / Pursuing internal rewards options with Force / Lobbying HMG for changes to HMRC regulations / Support for training of Specials / Membership of the Police Federation	Local Policing	Jul-21	Ongoing	Matthew Barber	TBC	On track
Governance	072	Develop, maintain and monitor an effective management information dashboard within the OPCC	OPCC Governance	Aug-21	Ongoing	Gillian Ormston	Gary Evans	Not commenced	PH to arrange meeting with GE and relevant SMG members (VW, HW & CM).
Governance	074	Produce and publish the PCC’s Annual Report 2020-21	OPCC Governance	May-21	Jun-21	Gillian Ormston	Gary Evans	Completed
Governance	075	Produce and publish the PCC’s Annual Report 2021-22	OPCC Governance	May-22	Jun-22	Gillian Ormston	Gary Evans	Completed	TV OPCC internal deadline for publication: 30 June 2022. GE compiling content. First draft to be made available by end of May 2022. Final version published and submitted to Police and Crime Panel for review at its meeting held on 24 June 2022.

Governance	076	Maintain a regular ‘environment scanning’ regime to highlight relevant policy and service initiatives and sources of intelligence on emerging threats, risks or opportunities relevant to: / informing the development and ongoing annual review of strategic priorities to be presented and delivered in the PCC’s Police & Criminal Justice Plan / informing & updating action tasks to be included in the OPCC Risk Register and Strategic Delivery Plan	OPCC Governance	May-21	Ongoing	Vicki Waskett	Gary Evans	On track	Briefings currently prepared and circulated on a weekly basis
Governance	077	Draft the 2022/23 OPCC Strategic Delivery Plan, including review of staff capability, capacity and development needs.	OPCC Governance	Feb-22	Mar-22	Gillian Ormston	TBC	Completed	Process - 2021/22 SDP rolled-over, updated & re- configured as a 4 year rolling Plan (2021-2025) to align with PCC's Police & Criminal Justice Plan, splitting presentation and reporting between ad hoc 'Project & Annual' actions, and ongoing 'Business as Usual & Cyclical' actions. SDP to be reviewed and updated on an ongoing basis, i.e. to be maintained as a 'dynamic' performance management tool.
Governance	078	Develop, agree and publish the 2020/21 Annual Governance Statement (AGS).	OPCC Governance	May-21	Jun-21	Gillian Ormston	Vicky Waskett Ian Thompson	Completed	AGS submitted to and endorsed by the JIAC at its meeting held on 18 June 2021
Governance	079	Oversee implementation of agreed actions contained in the 2020/21 AGS Action Plan.	OPCC Governance	May-21	Mar-22	Gillian Ormston	Vicki Waskett	Completed	No actions identified
Governance	082	Support PCC's role as Joint APCC Lead for Policing Performance Portfolio, including APCC representation on the national Crime and Policing Performance Board	OPCC Governance	Jul-21	Ongoing	Gillian Ormston	Gary Evans	Completed	GE support role confirmed
Governance	083	Support PCC's role as APCC Lead for Digital, Data & Technology Portfolio, including APCC representation on the national Strategic Change and Investment Board	OPCC Governance	Jul-21	Mar-22	Gillian Ormston	Gary Evans	Completed	GE support role confirmed [NB PCC Matthew Barber has now relinquished this role]
Governance	084	Identify needs and provide appropriate training for OPCC staff including through the PDR process	OPCC Governance	Oct-21	Ongoing	Gillian Ormston	TBC	Completed	Ongoing review of needs via annual PDR process and 'as & when' relevant training courses / seminars, etc. are identified
Governance	085	Support ongoing emergency services collaboration and prepare for fire governance changes if mandated by HMG	OPCC Governance	Jun-21	Ongoing	Matthew Barber	Gillian Ormston	On track	Meetings held between PH and 3 TV chief fire officers (CFOs) to consider potential respective work programme implications in event of any change in Fire & Rescue Services governance arrangements. As at 18 May 2022, Home Office released a consultation document to seek views on future FRS governance options prior to publication of White Paper. TV PCC will be submitting a response to the consultation paper.
Governance	086	Implement and maintain improved recording of OPCC decision making	OPCC Governance	May-21	Ongoing	Gillian Ormston	Vicki Waskett	Completed
Governance		Review and update the TVP/PCC Joint Corporate Governance Framework (JCGF) in readiness for 2022/23.	OPCC Governance	Jan-23	Ongoing	Matthew Barber	Vicki Waskett	On track	Due to be commenced in January 2022.
Governance		Prepare and draft the AGS for 2021/22	OPCC Governance	Jan-23	Ongoing	Matthew Barber	Vicki Waskett	On track	Due to be commenced in January 2022.

Governance	088	Review and maintain OPCC compliance with the Data Protection Act 2018 and General Data Protection Regulation (GDPR) requirements.	OPCC Governance	May-21	Ongoing	Vicki Waskett	Sierra Reid	On track	GDPR compliance is continually monitored with any new projects being subjected to screening questionnaires followed by Data Protection Impact Assessments where appropriate. The Chief Constable and the PCC have both signed an updated Information Sharing Agreement and Data Processing Agreement which regulates the flow of data between the Force and the PCC providing a high level of GDPR compliance. The breach register is regularly updated and staff are reminded at staff meetings about data breach procedures and GDPR processes to maintain awareness.
Victims	106	Provide management oversight to the Victims First Hub to ensure effective and consistent service is delivered to victims	Criminal justice	Nov-21	Ongoing	Helen Wake	Eddie Fitzpatrick	On track	Ongoing via: weekly VFH Manager (VFHM) & VFH Team Leader (VFHTL) meetings, weekly data quality review & feedback, monthly performance review (VFHM, VFHTL & Data Quality Officer (DQO)). A Wider Review is underway to redefine VF Hub processes and develop a range of outcome measurements to support quality provision.
Victims	107	Develop and maintain a Business Continuity Plan to support resilience of Victims First Hub under a range of supply/demand pressures	Criminal justice	Nov-21	ongoing	Helen Wake	Eddie Fitzpatrick	On track	Hub Resilience Plan has been developed in response to COVID and which is subject to ongoing review and update as the situation evolves. The plan is currently being updated to add VFH response to Major Incidents
Victims	108	Develop and maintain Victims First Hub risk register	Criminal justice	Nov-21	ongoing	Helen Wake	Eddie Fitzpatrick	On track	the risk register is a live document that is reviewed regularly.
Victims	110	Learning & Development Plan to ensure Victims First Hub maintains a sufficient level of training and all staff have the skills, experience and support to undertake their role effectively	Criminal justice	Nov-21	ongoing	Helen Wake	Eddie Fitzpatrick	On track	Training & Development Plan for Hub staff at all levels has been completed which includes core training competencies
Victims	111	Contract management of core victims services and the DA/SV grant funding	Criminal justice	Aug-21	Ongoing	Helen Wake	Wendy Walker and Candy Heinrich	On track	Contract monitoring takes place on a quarterly or 6 monthly basis, dependant on the value and risk of the contracted provision.

Police and Criminal Justice Plan Level 2 Meeting Data Review

1

All Crime Overview

A Focus on Crime Prevention, Reducing Levels of Neighbourhood Crime and Antisocial Behaviour

National position* 9th of 43
All Victim Based Crime – Longitudinal Data
MSG position* 3rd of 8

The volume of all crime recorded in the Force has increased by 9% YTD compared with 2021/22. This has remained the same as the last reported figures in July.
There continues to be notable increases in the recorded volume of Violence with and without Injury (+8% and +9% respectively). However there are also increases in volume crime types with vehicle crime increasing by 26%, all other theft by 22%, theft from person by 19% and criminal damage by 11%, YTD.
Longitudinal data for ASB is not comparable due to the change of recording system between Command and Control and CMP, however the monthly volumes since October 2020 are consistent with seasonal patterns.
*victim based crimes per 1000 population 12 months to June 2022

All Crime Overview
A Focus on Crime Prevention, Reducing Levels of Neighbourhood Crime and Antisocial Behaviour

		Recorded crime in Thames Valley 1st April 2021 to 31st August 2022
Strategic Plan Aim	Measure of Success	2021/22	2022/23	Thames Valley / Change	National position*	MSG position*
1	A 5% reduction in the volume of Violence with Injury (including DA but excluding knife crime)	7,083	7,671	8%	4th of 43**	3rd of 8**
2	A reduction in homicide levels against the 5 year average	8 / (5 year average excluding 2020/21)	8	-	14th of 43	4th of 8
3	A 5% reduction in the level of knife enabled crime, as defined by the Home Office (excluding possession)	530	549	4%

*crimes per 1000 population 12 months to June 2022
** Violence with injury (ONS)
forces’ operational autonomy.

Priority Measure	National Metrics	Baseline (Jul‐18 to Jun‐19)	Latest 12 months (Aug‐21 to Jul‐22)	% Change compared to baseline
Reduce Murder and other Homicides	Homicides	13	20	+54%
Reduce Serious Violence	Hospital admissions of u25s for assault with a sharp object	NHS data
	Offences involving a discharge of a firearm	39	16	‐59%
Disrupt drugs supply and county lines	Drug‐related homicides	1	3	+200%
	Police referrals into drug treatment	UK Health Security Agency data (formerly PHE)
Reduce Neighbourhood Crime	Burglary, robbery, theft of and from a vehicle, theft from a person	27,736	20,753	‐25%
Improve satisfaction among victims, with a particular focus of domestic abuse	Satisfaction with the police among victims of domestic abuse	CSEW
	Victim satisfaction with the police
Tackle cyber crime	Confidence in the law enforcement response to cyber crime	Cyber Aware Tracker
	Percentage of businesses experiencing a cyber breach or attack	Department for Digital, Culture, Media and Sport survey

The National Outcomes framework is national and measured at a national level, the data is not broken down to, or available on an individual force basis.

All forces are developing proxy measures to understand local context of the national measures.

TVP are working with regional colleagues to align proxy measures.

Call Handling: 101

Average time taken to answer 101 calls / proportion of callers waiting over 10 minutes for their call to be answered.

Over the last year, each month has averaged over 3 minutes to answer 101 calls.
In August the figure sits just below 10 minutes. The year-to-date figure is:
# 7 minutes

Over the last year, each month has seen the proportion of callers waiting over 10 minutes for their call to be answered at over 10%.
In the month of August, 34% of callers waited over 10 minutes for their call to be answered. The year-to-date figure is:
# 26.5%

Serious Organised Crime ‐ OCGs
#### isruptions and successful prosecutions for serious organised crime (SOC), Ensuring focus on acquisitive crime and exploitation
Disruptions by Threat Type (Apr – Aug 2022)

Increasing the number of d SOC groups involved with

IS
Disruptions – Grading type changes
(YTD vs 2021)
There has been an increase in the number of disruptions when compared with the same period last year. Drug threats remain the most significant focus of our disruptions, while modern slavery, firearms, and money laundering activities have seen notable increases in disruptions.
Disruptions by month
Source: APM

Fighting Cyber Crime and Fraud

Action Fraud

*Crimes recorded on Niche as “Action Fraud”	7
The Central Fraud Unit has recently commenced and has 10 of the first 20 officers in post and 10 due to start by January. The unit is on course to be fully staffed with 4 Sergeants and 32 Constables by 01/04/2023.

All fraud and cyber related fraud investigations for TVP will be conducted from the central
unit taking work away for ICR and providing an expert response to this crime type.

Whist the team is forming there is a focus on improving Op Signature performance which is now in the high 80% attendance compliance.

The Power BI Fraud toolkit is now in use meaning fraud and cyber figures for TVP can be analysed to monitor performance.

8

Increase the volume of formal action taken in rape & other sexual offences

#### Between April and August 2022/23 the Force took formal action in 53 rape offences, 3 more than in the same period last year which makes up 6% increase. The increase in FAT outcomes combined with 6% reduction in crimes has brought TVPs FAT rate from 5% to 6%
FAT Outcomes	2021/22	2022/23		% Change
Thames Valley	50	53		+ 6%

LPA	FAT rate
	2021/22	2022/23
Thames Valley	5%	6%

Context: TVP is ranked 18th nationally and 2nd in MSG for rolling 12 months positive outcome rate. This is a 1 position improvement for both national and MSG since Q1. YTD the Force achieved court resolutions for 45 rape offences. The reduction in the volume of rapes YTD compared to the same period last year are mainly driven by offences on under 16s.

Monthly FAT Rate

Increase the volume of formal action taken in rape & other sexual offences

#### YTD for 2022/23 the Force took formal action in 472 Other Sexual Offences, this is an increase of
+54.2% (+166) on the same period last year. YoY increase in FAT outcomes is outpacing the increase in crimes (+10%) hence the FAT rate has improved from 18% to 25%.
outcome type
2021/22	2022/23	% change

court disposals	98	175	+ 79%
OOCD	20	35	+ 75%
transferred to other agency	188	262	+ 39%

Context: TVP ranked 6th nationally and 3rd in MSG for rolling 12 months.
YTD for 2022/23 TVP achieved 175 court disposals this is an increase of +77 (+79%) disposals compared to the same period last year. OOC Disposals increased by +15 (75%) and the Force disposed of +74 (+39%) more incidents to another agency (Code 20).

OSO crimes increased primarily in sexual assault on a female over 13 (+194) and males over 13 (+45). The highest FAT volumes were achieved in Sexual Assault on a female over 13 (+133) and Sexual activity with a female child under 13 (+36).

Monthly FAT Rate

Domestic Abuse
### Working with other criminal justice agencies to improve performance in dealing with crimes such as domestic abuse, rapes and serious sexual assaults

Strategic Plan Aim	Measure of Success	Last updated	Thames Valley
10	A 10% increase in the volume of DA cases where formal action is taken	04/09/2022	41%
12	Increase the volume of formal action taken in stalking & harassment offences		46%
13	Monitor overall volume of VAWG offences & FAT rate		Offences +8% / FAT rate +3%
Monitoring	Arrest rate in DA related crimes that resulted in attendance		54%

Bringing offenders to justice

### Increasing successful outcomes through the criminal justice system

Strategic Plan Aim	Measure of Success	Last updated	Thames Valley	National position*	MSG position*
8	Achieve an increase in FAT volumes in rural crime	03/09/2022	150%^	Not available at national level
9	A 8% increase in overall volume of cases where formal action taken		18%	14th of 43	3rd of 8

^There have been 25 FAT outcomes between April – August 2022 compared to 10 for the same period the previous year
*Positive outcome rate 12 months to June 2022

There is ongoing work in this area to address a number of issues. These relate to;
‐	Data quality and the need to reduce duplicate records
‐	Engagement with LPAs and SPOCs to assist with record management
‐	Templates created to record measurable information such as powers used and details of person(s) involved
Recently, a critical incident was declared as the result of an Unauthorised Encampment in Milton Keynes. Learning from this is soon going to be disseminated to the wider Force to help with decision making and enhance knowledge in this area.
Unauthorised Encampments

Data Source: Thames Valley Police Crime Recording System: NICHE RMS Date Extracted: 07/09/2022
Note: The table/chart is representative of those occurrences where the occurrence type matched 'Unauthorised Encampment'.

Organisational Performance – key indicators
SP
### We value our workforce, make best use of resources and maximise the benefits of digital developments

Strategic Plan Measure	Measure of Success	Last updated	Thames Valley
1	Resourcing to establishment levels, particularly for ICR, detectives, neighbourhood and contact management teams	16/9/2022	Currently a -2.61% vacancy factor regarding overall police officer establishment. This has improved since May, when a -4.1% vacancy factor was reported.
2	Maintenance of reduced levels of avoidable attrition Forcewide with a focus on frontline officers & staff.		YTD total Q2 staff leavers is 156.15 (11.4% avoidable). / YTD total Q2 officer leavers is 114.01 (5.8% avoidable) / YTD total Q2 PCSO leavers is 27.74 (12.7% avoidable)
3	Increased retention and representation for BAME officers and staff forcewide		Force wide ethnic minority representation for staff is 6.1% and officers is 6.2% as of June 22.
5	Maintenance of the reduced levels of sickness of the previous 12 months		Overall hours lost due to sickness for Q2 is 163,599. This is a 50% decrease from Q1 22/23 (326,558).
7	Reduction in spending of overtime		We are £696k overspend YTD with a spend of £3.104m against a YTD budget of / £2.407m. 43% of the budget has been spent with four months of overtime paid.
12	Reduction in backlogs of digital forensic examination		Backlogged cases have increased for the first time in 6 months by 9% (553 to 605). The number of backlogged cases and exhibits in ACESO have particularly increased due to loss of staff.
			Last quarter there were an average of 4

#### 34

Report for Information

Title: Decisions Under the Scheme of Governance

Executive Summary:

This report details the decisions that have been taken in accordance with the Scheme of Governance in the period 1st July 2022 to 31st August 2022.

Recommendation:

The PCC is asked to NOTE the decisions taken by Chief Officers during the period 1st July 2022 to 31st August 2022.

Police and Crime Commissioner

I hereby approve the recommendation above.

Signature	Date

Page 1 of 4

PART 1 – NON-CONFIDENTIAL

Introduction and background

  1. The Scheme of Corporate Governance sets out the formal delegations made by the Police and Crime Commissioner (PCC) and the Chief Constable to senior officers to facilitate the efficient running of the business, hence avoiding unnecessary delays in decision making. The PCC has given consent for the Chief Constable to enter into contracts and to acquire or dispose of property, other than land, subject to the requirements of Financial Regulations.

  1. The Scheme of Governance includes a requirement for all decisions statutory officers make under the powers given to them by the PCC and Chief Constable to be recorded and be available for inspection.

Issues for consideration

Financial Regulations

  1. Approval of Tenders/Contracts

Financial Regulations delegate decisions for the acceptance of tenders/award of contract for goods and services.
    1. Up to £200,000: to the appropriate chief officer (Director of Finance)
    2. From £200,000 up to £1m: the appropriate chief officer from the PCC’s office and the Force (PCC’s Chief Finance Officer or Chief Executive and the Force Director of Finance)

Appendix A details the decisions taken following a full tender exercise:
    1. £50,000 to the £200,000, authorised by the Director of Finance/Head of Procurement 3 tender/contract decisions totalling £414,740.
    2. between £200,000 and £1m, authorised by the Director of Finance and PCC’s Chief Finance Officer no approvals this period.

  1. Single Quotation/Proprietary Article or Service

Financial Regulations also provide for exceptional circumstance where it is in the interests of Thames Valley Police (TVP) not to seek competitive tenders. This covers those circumstances where it has been established that:
    1. there is only one source of supply, or
    2. the works, goods or services required are of such a special nature that no advantage would accrue by inviting competitive tenders where only one supplier can provide the service or
    3. the works, goods or services are urgently required and loss, injury or damage could occur through a delay in advertising.

Appendix A details 5 instances totalling £1,028,548 where this delegation has been utilised.

  1. Disposal of Assets

In accordance with the Asset Management Strategy the Chief Constable is responsible for disposing of police houses with an estimated sale value of less

Page 2 of 4

than £0.5m. Properties with an estimated sale value of more than £0.5m require the approval of the PCC. No houses were identified for sale in the period 1st July
– 31th August 2022.

People Service Functions

The Scheme of Governance includes a number of delegations from the Chief Constable to the Director of People to facilitate effective day to day management. During the period in question 6 applications were granted to extend occupational sick pay on behalf of members of police staff. There have been no redundancy claims with pension strain paid during this period.

Legal Functions

The scheme of governance authorises the Head of Legal Services to approve the settlement of any claim (including Employment Tribunal claims) brought against the Chief Constable or the PCC, or the making of any ex gratia payment:
  1. Ex Gratia and Damages payments up to £10,000:	Head of Legal Services.
  2. Damages - £10,000 - £30,000: Head of Legal Services with the PCC’s Chief Executive or Chief Finance Officer.
  3. All other settlements must be approved by the PCC.

  1. Employment Tribunal settlements – 1 settlement has been made in this period.

During the period 1st July – 31st August 2022 the following payments have been made:
  1. Under Public Liability - 16 payments under £10,000 have been made totalling £37,592
  2. Under Employers Liability – 1 payment has been made totalling £5,000.
  3. Ex-gratia payments – 8 payments have been made, all for less than
£10,000, totalling £5,813.
  1. Employment Tribunal settlements – 1 settlement has been made in this period for £9,000.

Financial comments

  1. All financial commitments as a result of the above delegations were within the current revenue budgets.

Legal comments

  1. The scheme of delegation has been complied with in all cases.

Equality comments

  1. No specific implications arising from this report

Page 3 of 4

Background papers

Public access to information
Information in this form is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.
Is there a Part 2 form? No

Name & Role	Officer
Head of Unit / The report lists all actions taken under delegated powers during the period 1st July and 31st August 2022.	Director of Finance Director of People
Legal Advice / Relevant delegations are set out in the agreed Framework of Corporate Governance as approved by the PCC and Chief Constable on 1st April 2014	Chief Executive
Financial Advice / All awards and payments have been contained within existing budgetary provisions	PCC Chief Finance Officer
Equalities & Diversity / No specific implications arising from this report	Chief Executive

STATUTORY CHIEF OFFICERS’ APPROVAL

We have been consulted about the proposal and confirm that financial and
legal advice have been taken into account in the preparation of this report.

We are satisfied that this is an appropriate request to be submitted to the Police and Crime Commissioner.
Chief of Staff OPCC
Date: 22nd September 2022
Chief Finance Officer PCC
Date: 22nd September 2022

Page 4 of 4
#### 39

Financial Regulation - Delegated Authorities
Financial & Contractual Decisions under the scheme of Governance 1st July - 31st August 2022
Contracts/Approval of tenders	Awarded to	Date	Cost/Value	Duration
£50,000 to £200,000			£
Gates and Barriers	Century	06/07/2022	125,000	12 months
FIU Relocation QS Contractor	Pick Everard	06/07/2022	165,000	12 months
Support for the transfer of data to Azure from ARK	ANS	31/08/2022	124,740	12 months + 12 months ext
Total Value
414,740
£200,000 to £1m
Total Value			0
Single /Proprietary/Concession £50k and above					Rationale
CCN - Grounds Maintenance Services Extension Contract	Idverde	01/07/2022	64,426	4 months	Continuation Service
SSA - Gray key Licensing in both HTCU and SEROCU	GrayShift	06/07/2022	68,100	12 months	Single Supplier
Grant - STAR Bid Youth Justice Video project	Lime	18/07/2022	70,000	9 months	Single Supplier
Concession - IA Consultant	Illuminet	04/08/2022	98,000	6 months	Urgency
Concession Genesys & Access Contracts	ADT	26/08/2022	728,022	24 months	Continuation Service
Total Value			1,028,548