OFFICE OF THE POLICE & CRIME COMMISSIONER FOR THAMES VALLEY

Report for Decision: PCC 2022-P-017

Title: Contract for the supply of Forensic Investigation Unit, Gowell Farm Development - Main Contractor Works

Executive Summary: / TVP have forensic investigation teams spread over a number of sites within the force area. G block on the HQ South site houses a number of these teams, but is now at the end of its economic life, and replacement is required as a matter of urgency. Additional teams are located within HQ South, Langford Locks, Bicester Traffic Base, St Aldates, Abingdon and Banbury Police Stations. / A Lead Design Consultant was appointed in December 2021 to deliver 3 design options that would deliver a consolidated single site for the Forensic Investigation Teams. / Following approval of the preferred option at the Strategic Estates Group on 25 April 2022 this report proposes the appointment of a main contractor. / The appointment of the Main Contractor was over 2 contract stages as follows:- / The first stage being a Pre-Construction Services Agreement (PCSA) to work with the Lead Consultant and appointed Quantity Surveyor (QS) in developing a full design solution that could be then be fully designed and costed by the Main Contractor. The PCSA is to bring the main contractor into the general design input for their knowledge on materials market options and issues. / The second stage is to appoint the Main Contractor under the Joint Contracts Tribunal (JCT) Forms of Contract for construction, for the works programme. TVP has the option at this stage to appoint the stage 1 Main Contractor (after approval of full works costs) or go back to market to source a new Main Contractor. / Full details are provided in Annex 1.

Recommendation: / The Police and Crime Commissioner is invited to agree the award of a contract for the supply of a Forensic Investigations Unit at Gowell Farm, Bicester, main contractor works to Willmott Dixon Construction. / The above contract is for an initial term of Pre-Construction Services Agreement (PCSA) of 7 months duration with the option to award the main works contract (after approval) for 24 months duration from January 2023. / The total value of this PCSA contract including the early Design Services, is estimated at £135,613. This is broken down as £35,613 for the PCSA and £100,000 for early design packages.

Police and Crime Commissioner / I hereby approve the recommendation above.
Signature Date: 5 July 2022

PART I – NOT CONFIDENTIAL

Introduction and background

  1. TVP have forensic investigation teams spread over a number of sites within the force area. G block on the HQ(S) site houses a number of these teams, but is now at the end of its economic life. Replacement is required as a matter of urgency. Additional teams are located within HQ(S), Langford Locks, Bicester Traffic Base, St Aldates, Abingdon and Banbury Police Stations.

  1. A Lead Design Consultant was appointed in December 2021 to deliver 3 design options that would deliver a consolidated single site for the Forensic Investigation Teams that would be discussed with a decision being made at the Strategic Estates Group (SEG) Meeting on 25th April 2022. At this meeting it was agreed to proceed with the 3rd Option. The 3 options being:-

- Option 1 – Basic/ Minimum requirements; Basic space for the Forensic Teams from HQS & Langford Locks, no allowance/ space for future expansion, limited welfare and facilities.
- Option 2 – Enhance Requirements; Space for the Forensic Teams from HQS & Langford Locks with limited space for future expansion, incorporate additional welfare facilities and a gym for the wider Bicester Team.
- Option 3 – Expanded Requirements; In addition to space for Forensic Teams from HQS & Langford Locks, will also include POLIT Abingdon, CSI Banbury and CSI Loddon Valley, space for future expansion 10-15%, incorporate additional welfare facilities and a gym for the wider Bicester Team.

  1. The SEG agreement was to proceed with the tendering process to appoint the Main Contractor to deliver option 3.

  1. The appointment of the Main Contractor was over 2 contract stages as follows:-

The first stage being a Pre-Construction Services Agreement (PCSA) to work with the Lead Consultant and appointed Quantity Surveyor (QS) in developing a full design solution that could be then be fully designed and costed by the Main Contractor. The PCSA is to bring the main contractor into the general design input for their knowledge on materials market options and issues.

The second stage is to appoint the Main Contractor under the Joint Contracts Tribunal (JCT) Forms of Contract for construction, for the works programme. TVP has the option at this stage to appoint the stage 1 Main Contractor (after approval of full works costs) or go back to market to source a new Main Contractor.

  1. Full details are provided in Annex 1.

Issues for consideration

  1. The Tendering process which covered both stages of contracting, was conducted by Procurement Services under the Southern Construction Framework. The process covered Main Contractor 1 (MC1) – Selection / Shortlisting on key questions about the experiences and skills of contractors. Main Contractor 2 (MC2) – Formal Tender was to seek bids from the shortlisted contractors which were evaluated by Procurement and Property Services personnel on 40% Cost, 50% Deliverables and 10% Presentation.

  1. It should be noted that the MC1 evaluation did not proceed due to the number of contractors bidding was below the given number (4) required to be shortlisted. A concession was granted and as all 3 MC1 bids were compliant they were taken through the MC2 automatically. All bidders were notified of this decision.

  1. Following the completed evaluation process this paper seeks authority to appoint a Main Contractor for the PCSA and early design packages. The Authority to seek approval for the main construction JCT contract will be sought when full design has been approved and full costs have been developed, which is expected for the December 2022 SEG meeting.

  1. Whilst the total cost of PCSA and Estimated Construction has been used in evaluation it is only the PCSA and the Contractor’s Design Elements that require early specialist early design package input, (which includes: Mechanical Electrical and Plumbing (MEP), Ground works, Façade and Pre-fabricated structures), that are being committed to under this Commercial Outcome Report. A provisional amount has been included in this Report for the specialist design input and the Main Contractor is to tender these key packages in order to secure the best value tender for these works at an early PCSA stage.

  1. The evaluation summary is provided below:

Financial comments

  1. The contract for pre-construction stage works focuses on design and costing. There is a budget allocation of £2.1m within the overall £18m project fund specifically for the design works. While this contract is only one element of the total design process and costs, this contract is covered by the allocated funds and is not considered a risk of overspend

Legal comments

  1. The contract is being awarded via a legally compliant framework

Equality comments

  1. There are no specific issues with regard to Equality & Diversity with this award.

Background papers
   n/a

Public access to information Information in this form is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.
Is there a Part 2 form? Yes

Name & Role	Officer
Head of Procurement	Richard Fowles
Financial Advice	Linda Waters

PCC’S STATUTORY OFFICERS’ APPROVAL
We have been consulted about the proposal and confirm that financial and legal advice have been taken into account in the preparation of this report. / We are satisfied that this is an appropriate request to be submitted to the Police and Crime Commissioner. / Chief Executive Date: 5 July 2022 / Chief Finance Officer Date 5 July 2022