OFFICE OF THE POLICE & CRIME COMMISSIONER FOR THAMES VALLEY

Report for Decision: PCC 2021-P-015

Title: Contract for the supply of a Works Contract (main works) at Atlantic House, Reading

Executive Summary: / This initiative is to carry out the refurbishment works at Atlantic House, Reading. Atlantic House is being developed to be the main TVP Berkshire LPA building, replacing the main building in central Reading which has been sold to a private developer. / In 2019 a competitive tender process was carried out under the Southern Construction Framework to source a Contractor to carry out the Refurbishment Works, including design input, for the new Regional LPA building in Reading – Atlantic House. Midas Construction was selected and a Pre-Contraction Agreement was awarded to them for their engagement into the design works. / Once the design process was concluding the preferred contractor was required to quote for the enabling works element that covered clearing out existing areas of Atlantic House and preparation for the main works to complete. Value £880,244. / This report now seeks approval for the main refurbishment works, at a cost of £8,081,949, that formed part of the original tender requirements. / Full details are provided in Annex 1

Recommendation: / The Police and Crime Commissioner is invited to agree the award of contract in respect of the above to Midas Construction Limited / The programme for the main works falls in-line with the overall works programme. / The total value of this contract is estimated at £8,081,949 for the main works only.

Police and Crime Commissioner / I hereby approve the recommendation above.
Signature Date: 15 June 2021

PART I – NOT CONFIDENTIAL

Introduction and background

  1. This initiative is to carry out the refurbishment works at Atlantic House, Reading. Atlantic House is being developed to be the main TVP Berkshire LPA building, replacing the main building in central Reading which has been sold to a private developer.

  1. The procurement of the main contractor for the Atlantic House Refurbishment Works was on an agreed strategy of using the Southern Construction Framework for a traditional two-stage procurement package. The traditional procurement route is based on the client (TVP) retaining design responsibility as opposed to a design and build contract where the main contractor is responsible. The traditional procurement route allows for early engagement of the successful contractor for input into the design whereby they can advise on methods and materials, but with minimal risk on contractor engagement and fees before final design approvals.

  1. The two-stage process entailed Southern Construction Framework team completing a capability assessment with all contractors, on the relevant lot, to shortlist to invite to tender under mini competition.

  1. TVP Procurement and Property Services carried out a mini competition tender with the three short listed contractors (from capability assessment) to identify the preferred contractor that TVP would engage with going forward. Following evaluation, Midas Construction Limited were selected and they were awarded a Pre-Construction Services Agreement – for their input for pre-design - with an initial value of £27,736.

  1. Once the design process was concluded, the preferred contractor was required to quote for the enabling works element that covered clearing out existing areas of Atlantic House and preparation for the main works to complete. Value £880,244.

  1. Following approval of the final designs, the preferred contractor was required to fully cost and submit a “tender” to carry out the works. This tender has been evaluated by the appointed Quantity Surveyor (QS). Following a number of clarifications, the QS recommends the award of contract to the preferred contractor, Midas Construction, in the sum of £8,081,949.

  1. Full details are provide in Annex 1.

Issues for consideration

  1. Midas has obtained sub-tenders for each package of work. In the majority of cases, 3 tenders have been received and evaluated. Some packages have only received 2 sub-tenders and a few specialist work areas are based on a single tender submission.

  1. The appointed Quantity Surveyor, Ridge, has scrutinised all individual tender packages and has produced a comprehensive tender report for Property Services. They have concluded that a thorough tender process has taken place and appropriate evidence has been provided and checked.

  1. The tender is close to the approved budget and has been agreed as being affordable.

Financial comments

  1. The total value of this element of the contract is estimated at £8,081,949.

  1. Total spend to date, plus commitments is therefore £8,989,929

  1. The overall capital project budget for this scheme is £9.5m

Legal comments

  1. This contract is being let following an open tender process to select the preferred contractor

Equality comments

  1. No specific implications arising from this report.

Background papers
   n/a

Public access to information Information in this form is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.
Is there a Part 2 form? Yes

Name & Role	Officer
Head of Procurement	Richard Fowles
Financial Advice	Linda Waters

STATUTORY OFFICERS’ APPROVAL
We have been consulted about the proposal and confirm that financial and legal advice have been taken into account in the preparation of this report. / We are satisfied that this is an appropriate request to be submitted to the Police and Crime Commissioner. / Chief Executive Date: 15 June 2021 / Chief Finance Officer Date 15 June 2021