Procurement Services

Procurement Outcome Report

TVP Reference PR19006

Contract for the supply of Western Hub, Theale – Works Contract – Fit Out Works

Submitted By: Neil Smith

Date Submitted: 30th September 2021

# Contract Award (and POR) Sign-Off Sheet

By approving this document the Procurement Governance Board confirms acceptance of the detail contained within this document, approval to proceed with contract award, implementation and realisation of the benefits.

In the case of a Procurement which results in a new contract (or extension) the document replaces the previous award paper, and has a section for the relevant sign-offs below.

Part 1 –
For publication on TVP / PCC Internet Site

Public access to information Information in this POR is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.

Executive Summary and Recommendations
BACKGROUND / 1.1.1 Project Budget £4,500,000 Subjective Codes: AA118 / 1.1.2 Summary of requirement and process: / Background - In May 2020 a competitive tender process was carried out under the Southern Construction Framework to source a Contractor to carry out the Refurbishment Works, including design input, for the new Western Hub. Midas Construction were selected and a Pre-Contract Services Agreement was awarded to them for their engagement into the design works. The approved POR and supporting approvals are here, to note the original award was for only £12,492 so did not require formal POR approval. However, a strategic paper was written to ensure that the correct strategy was understood and agreed. / No formal approval of contract has been given for the actual works or values following the acceptance of the above POR. / Midas were then awarded the enabling works contract. The POR and Approvals for this are here: / Current Position - TVP has now reached the stage where the design is complete and a Contract Sum for the fit-out works has been agreed. / Within the original procurement process TVP retained the option to re-tender the fit out contract if it was felt that the proposal from the main contractor (Midas) did not offer value for money. Having considered the time it would take to re-tender the works causing a 3 month delay and the current volatile market within the UK construction industry it is felt that these any further delays in awarding a contract would have further negative impacts on the contract value. Therefore, it is believed that the award of contract to Midas reduces any further risks on the budgetary impact of the completed project, and offers value for money at this time. / This POR seeks approval for the fit-out works at a cost of £5,172,035 that formed part of the original tender requirements (PR19006 strategic outcome report (first embedded document on this POR)). Midas have formerly quoted for these works which have been reviewed and assessed by TVPs QS for the project. A full tender report is available in part 2 of this report. / 1.1.3 Regulation 84 form has been completed and is at Appendix A (Note that by default a regulation 84 form should be completed in all circumstances). This is a record of the exercise required to be kept by the Cabinet Office. / 1.1.4 Contract Terms and Conditions: The suppliers meet all the requirements of the contract terms and conditions and specification and offer the Most Economically Advantageous Solution, as assessed through the evaluation process. / 1.1.5 Legal Implications: There are no legal implications in awarding the contract for the fit out works. The process is legally compliant. / 1.1.6 Equality and Diversity: There are no implications in awarding the contract for the fit out works on Equality and Diversity. / 1.1.7 Realisation Implementation Plan: Implementation Plan will be agreed as part of the overall works programme / 1.1.8 Contract Management Review: Tier 1 or Tier 2 or Tier 3 / 1.1.9 The procurement process has followed and complied with the 5 key Treaty Principles of PCR 2015:- Transparency; Non-Discrimination; Equal Treatment; Proportionality; Mutual Recognition. / 1.1.20 The accountant for the business area has reviewed this document and has advised that the value of the work at £4.982m is over the budget for this stage of the project by £0.5m.

# 1.1.10 Attachments
Please include the following attachments as additional supporting information:
 Supplier Scoring
Not Applicable
 Any additional Supporting information
1.2 RECOMMENDATION / 1.2.1 The Police and Crime Commissioner / Chief Constable of Thames Valley Police (Chief Finance Officer and Director of Finance) are invited to agree the award of contract in respect of the above Midas Construction Limited / The programme of fit-out works falls in-line with the revised overall works program / The total value of this contract is estimated at £5,172,035 for the fit-out works only.

Process and POR approval
Role	Name/Job Title or Shoulder Number	Signature and Sign-Off Date
Project Sponsor	Daniel Clarke C7893	Daniel.clarke@thamesvalley.pnn.police.uk / 02/09/2021
Procurement Business Partner	C6081	20.09.21
Procurement Lead	Des Dockerill C3760	Desmond.dockerill@thamesvalley.police.uk / 17/09/2021
TVP Finance	Dave Allen	David.Allen2@thamesvalley.pnn.police.uk 17/9/2021
Legal	N/A

Contract Award Approval
Approval Role	Name or Shoulder Number	Job Title	Signature and Sign-Off Date
Reviewer / Approver	Richard Fowles	Head of Procurement
First Approver:	Linda Waters	Director of Finance
Second Approver:	Ian Thompson	Chief Finance Officer
Third Approver:	Matthew Barber	OPCC

Contract Summary and Information for BLPD
Proposed Supplier (s)	Midas Construction Limited
Planned Contract Start Date	25 October 2021
Contract Duration – Initial Term (months)	30 Weeks
Contract Extensions Available (months)	None
Contract Value Initial Period (months)	£5,172,035
Contract Value Extension per extensions periods	£0.00
Collaborative Purchase Information (who are we buying with and what is there proportion of spend).	N/A

Project Savings (for use on Home Office benefits reporting – NOT TO BE INPUT ON BLPD)
Baseline Spend (highlight any changes to information provided in PLD)	No changes
Savings Enabled: / Detail at High, Low and Expected level if the savings are likely to be variable e.g. based on demand. / Include Annual & Total Contract Savings	Cashable:£N/A
	New Requirement
Savings Start Date if different from Contract start date	Cashable:£N/A
Collaborative Savings	N/A
Savings Types (based on Savings Definitions in Savings Analysis Worksheet)	Cashable:£N/A
Other Benefits:	N/A
Total Savings as a % of baseline spend:	Cashable:£N/A