OFFICE OF THE POLICE & CRIME COMMISSIONER FOR THAMES VALLEY

Report for Decision: PCC 2021-P-023

Title: Contract for the supply of Western Hub, Theale – Works Contract – Fit Out Works

Executive Summary: / In May 2020 a competitive tender process was carried out under the Southern Construction Framework to source a Contractor to carry out the Refurbishment Works, including design input, for the new Western Hub. Midas Construction were selected and a Pre-Contract Services Agreement was awarded to them for their engagement into the design works. / TVP has now reached the stage where the design is complete and a Contract Sum for the fit-out works has been agreed. / Given the increase in costs for these fit-out works, compared to the initial budget forecasts, a report was presented to, and agreed by, the South East Regional Collaboration Board on 2nd September 2021. / Full details are provided in Annex 1

Recommendation: / The Police and Crime Commissioner is invited to agree the award of contract in respect of the above Midas Construction Limited / The programme of fit-out works falls in-line with the revised overall works programme. / The total value of this contract is estimated at £5,172,035 for the fit-out works only.

Police and Crime Commissioner / I hereby approve the recommendation above.
Signature Date: 30 September 2021

PART I – NOT CONFIDENTIAL

Introduction and background

  1. In May 2020 a competitive tender process was carried out under the Southern Construction Framework to source a Contractor to carry out the refurbishment works, including design input, for the new Western Hub, a joint venture by police forces in the South East region

  1. Midas Construction were selected and a Pre-Contract Services Agreement was awarded to them for their engagement into the design works. Although the initial contract sum was relatively small (£12,492) a strategic paper was written to ensure that the correct strategy was understood and agreed.

  1. No formal approval of contract has been given for the actual works or values following the acceptance of the above contract.

  1. In March 2021 Midas were awarded the enabling works at the Western hub at a cost of £435,012.

  1. TVP has now reached the stage where the design is complete and a Contract Sum for the fit-out works has been agreed.

  1. Within the original procurement process TVP retained the option to re-tender the fit out contract if it was felt that the proposal from the main contractor (Midas) did not offer value for money. Having considered the time it would take to re-tender the works causing a 3 month delay and the current volatile market within the UK construction industry it is felt that any further delays in awarding a contract would have further negative impacts on the contract value. Therefore, it is believed that the award of contract to Midas reduces any further risks on the budgetary impact of the completed project, and offers value for money at this time.

  1. This PCC decision report seeks approval for the fit-out works at a cost of £5,172,035 that formed part of the original tender requirements. Midas have formally quoted for these works which have been reviewed and assessed by TVPs Quantity Surveyor for the project.

  1. Full details are provided in Annex 1.

Issues for consideration

  1. These fit-out works will cost significantly more than the initial estimate when the original Western Hub proposal was agreed by partner forces in the South East. As such, a report was presented to, and agreed by, the SE Regional Collaboration Board on 2nd September 2021.

Financial comments

  1. The fit-out works are estimated to cost £5,172,035. This will be funded by a combination of Home Office grant and partner contributions from other SE forces

Legal comments

  1. There are no legal implications in awarding the contract for the fit out works. The process is legally compliant.

Equality comments

  1. There are no implications in awarding the contract for the fit out works on Equality and Diversity.

Background papers
   n/a

Public access to information Information in this form is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.
Is there a Part 2 form? Yes

Name & Role	Officer
Head of Procurement	Richard Fowles
Financial Advice	Linda Waters

STATUTORY OFFICERS’ APPROVAL
We have been consulted about the proposal and confirm that financial and legal advice have been taken into account in the preparation of this report. / We are satisfied that this is an appropriate request to be submitted to the Police and Crime Commissioner. / Chief Executive Date: 30 September 2021 / Chief Finance Officer Date 30 September 2021