TVP Reference PR22013

OPCC Report for Decision PCC 2024-P-003

Contract for the Fit Out of Western Hub Building A

Gateway C: Commercial Outcome Report & OPCC Decision Report

Submitted By:

Date Submitted:

# Contract Award (and COR) Sign-Off Sheet

It is the responsibility of the Procurement Department to complete and present this paper to the CGB (this may be by a virtual process)

By approving this document the Commercial Governance Board confirms acceptance of the detail contained within this document, approval to proceed with contract award, implementation and realisation of the benefits.

In the case of a Procurement which results in a new contract (or extension) the document replaces the previous award paper, and has a section for the relevant sign-offs below.

Part 1 –
For publication on TVP / PCC Internet Site

Public access to information
The information in this COR is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.

Executive Summary and Recommendations
BACKGROUND / 1.1.1 Budgeted Spend: Overall £5.54M budget (exclude site acquisition) Subjective Codes: AA125 / 1.1.2 Summary of requirement and process: / TVP is looking to appoint a main contractor to complete the internal office fit-out and refurbishment works to the existing empty property (Building A) at Theale, West Berkshire. The agreed procurement process was to carry out a Mini Competition (further competition) under the Southern Construction Framework (SCF) for the early stage contractor services under Pre-Construction Services Agreement (PCSA) and ultimately the fit-out works contract subject to competitive package tendering under the PCSA and final costs approval. / Morgan Sindall been appointed following previous COR submission dated 22 August 2022 after a mini competition under SCF. The PCSA commenced in November 2022, Morgan Sindall have been working with the project team and sourced sub-contractors under an open book tender process. Due to site restrictions and economic reasons, the sub-contractors were selected base on the outcome of work packages tender of the adjacent site, Building C that each works package were tendered by three or more suppliers to demonstrate best value, same tender rates applied for the works in Building A. / At the end of January 2023, Morgan Sindall submitted their proposed contract sum for the fit-out works to Building A, which was significantly higher than original project budget due to market volatility and high inflation. Full tender review was carried out jointly by the Contractor, external consultant Quantity Surveyor and TVP Property Services Department, which including further market testing to major packages to ensure due diligence in regard to value for money. This resulted in a revised contract sum submission on 25 April 2023. However, due to budget reason, this tender offer was not accepted at the time, and subsequently the tender prices were revised again in December 2023 for the inflationary increase and resequencing of works. / This COR is now recommending the award of the construction contract to Morgan Sindall base on their latest contract sum offer following the work packages evaluation of the increased costs. The decision to award the contract will also allow the contractor to complete further specialist design and identify proposed value engineering outcomes. / 1.1.3 Regulation 84 form has been completed and is at Appendix A: N/A / 1.1.4 Contract Terms and Conditions: The suppliers meet all the requirements of the contract terms and conditions and specification and offer the Most Economically Advantageous Solution, as assessed through the evaluation process. / 1.1.5 Legal Implications: This contract will be awarded following tender under SCF. / 1.1.6 Equality and Diversity: There are no specific issues with regard to Equality & Diversity with this award. / 1.1.8 Realisation Implementation Plan. A full programme will be agreed with the recommend contractor upon award of contract. / 1.1.9 Contract Management Review: Tier 1 or Tier 2 or Tier 3 / 1.1.10 The procurement process has followed and complied with the 5 key Treaty Principles of PCR 2015:- Transparency; Non-Discrimination; Equal Treatment; Proportionality; Mutual Recognition. / 1.1.11 There is a confidential Part 2 form is for internal use and is not for publication into the public domain due to the sensitive/commercial nature of the information.

# 1.1.12 Attachments
Please include the following attachments as additional supporting information:
 Any additional Supporting information
# 1.1.13 FINANCIAL IMPLICATIONS
Budget is now in place and costs are shared with other forces. The value of contract tendered does not raise any specific financial risks

1.2 RECOMMENDATION / 1.2.1 The Police and Crime Commissioner / Chief Constable of Thames Valley Police (Chief Finance Officer and Director of Finance) are invited to agree the award of contract in respect of the above to Morgan Sindall for fit-out works to Building A. / The above contract is for a construction contract period of 32 weeks. / The construction budget to complete this construction contract over the full project period is £4,340,664; this sum comprises the current contract sum offer of £4,214,237, and additional allowance for construction contingency of £126,427.

Process and COR approval
Role	Name/Job Title/or Shoulder No.	Signature and Sign-Off Date
Project Sponsor (Stakeholder) / Approving the proposal as meeting the requirements	Daniel Clarke
Collaborative Organisation Stakeholder (other body).
Procurement Business Partner / Approving the award as meeting the commercial and regulatory requirements of the force	Ally Hughes
Procurement Lead / Confirming the process as meeting the objectives and regulatory requirements set	Dan Penny
TVP Finance / Confirming that they have approved the budgetary and financial implications of this proposal	Linda Wates
Legal (If applicable) / Confirming their review of any legal implications of this proposal	N/A

Approval Role	Name or Shoulder Number	Job Title	Signature and Sign-Off Date
Approver / Supporter / approving contract award up to a value of £200,000 and supporting values above £200,000	Richard Fowles	Head of Procurement	21.12.23
Approver / Supporter: / approving contract award up to a value of £1,000,000 and supporting values above £1,000,000	Linda Waters	Director of Finance	22.12.23
Consulted / Approver: / Consulted on contract award values of £200,000 up to £1,000,000 / Approval on contract award values above £1,000,000	Martin Thornley	OPCC - Chief Finance Officer	22.12.23
Approver: / Approval on contract award values above £1,000,000	Gillian Ormston	OPCC - Chief of Staff	21.12.23
Final Approver: / Approval on contract award values above £1,000,000	Matthew Barber	Police & Crime Commissioner	21.12.23

Contract Summary and Information for BLPD
Proposed Supplier (s)	Morgan Sindall
Planned Contract Start Date	19 February 2024
Contract Duration – Initial Term (months)	32 weeks
Contract Extensions Available (months)	As per JCT building contract if applicable
Contract Value Initial Period (months)	£4,214,237
Contract Value Extension per extensions periods	As per JCT building contract in applicable
Collaborative Purchase Information (who are we buying with and what is there proportion of spend).	N/A

Contract Savings (for use on Home Office benefits reporting – NOT TO BE INPUT ON BLPD)
Baseline Spend (highlight any changes to information provided in CLD)	£4,214,237
Savings Enabled: / Detail at High, Low and Expected level if the savings are likely to be variable e.g. based on demand. / Include Annual & Total Contract Savings	Cashable: N/A
	N/A
Savings Start Date if different from Contract start date	Cashable:N/A
Collaborative Savings	N/A
Savings Types (based on Savings Definitions in Savings Analysis Worksheet)	Cashable: N/A
Other Benefits:	N/A
Total Savings as a % of baseline spend:	Cashable: N/A