REPORT- ADDITIONAL FUNDING REQUEST
Atlantic House, Reading Refurbishment
Y E Hoo, Quantity Surveyor/Property Services Department
16/10/2024
PCC 2024 / 023

In summary

Construction works to refurbish Atlantic House for the relocation of Reading Police Station is in progress. The project has encountered various delays and numerous variations leading to extra costs. The current overall project cost forecasted to be around £21.08M, additional £1.97M funding over the approved budget of £19.11M is therefore required to complete the project.

Background

Following the liquidation of Midas in Jan 2022, a re-tender process was carried out using the Southern Construction Framework (SCF) and Willmott Dixon Constructions (WDC) were appointed. Total £19.11M project budget approved in Aug 2023 to resume works at Atlantic House, Reading.

Works and Programme Updates

Original planned start date for the construction works was 9/10/23 and completion by 2/9/2024. The actual start date delayed to 18/12/2023 to resolve outstanding tender offer queries. The construction works is currently progressing well on site and building works is approximately eighty percent completed with anticipated building handover by end of January 2025 and practical completion on 17/2/2025.

It is approximately 14 week extension of time granted to the original construction period mainly due to;
- delay of getting works insurance and additional strip out works; 2 weeks
- change of fire strategy and roof platform works; 12 weeks
Cost Impacts

The current cost forecast indicates £1.97M cost increase against the approved £19.11M project budge based on current anticipated final construction costs and allowances for fees and direct due to extended tender and construction period.

Main reason of the costs increase is due to large number of variations to the works and delays. Following initial review of the variation costs, substantial portion of these variations were;
- design developments
- element of detailed design not available prior to tender
- change of fire strategy and subsequent cost of delay
- further deterioration of building and works installed
- quality and warranty issue with works partially completed

WDC was engaged to work with the design team under Pre-Construction Services Agreement (PCSA) to review the design and scope of works prior to the final tender offer. There is an understanding that taking on a partially completed construction works is challenging, however, this level of variations and claims were not anticipated.

Consider there are large number of variations to review and not yet agreed, it is difficult to guarantee the final cost or certainly of any further increase especially with limited contingencies/ risk allowance in the new cost forecast.

Cost Control and Increase Scrutiny

Continuous costs review is carry out by our external cost consultant and tighter change control process is being placed for any new change request.

In generally, all variations are subject to challenge and assessed according to the building contract, the process includes;
- checking if it is a valid claim
- review with project team the actual extend of extra works
- challenge variation costs submitted and agreeing a reasonable costs
The cost consultant provides monthly cost update to TVP project team, which will be review by TVP Project Manager and Quantity Surveyor for further scrutiny.

Any new change request will have to include details of associated costs and programme impacts to obtain an informed decision from the Project Board.

The project team to review risk register and highlight potential risks to Project Board to provide early warning.

Additional Funding Request

In order to complete the project with 4 months left on programm, an additional £1.97M funding is required. Although it is not possible to guarantee that there will not be further additional cost at this stage, the project team is focus on cost challenge and working toward ascertain the final variations cost.

Decision
The PCC agreed to this additional funding request on 22 October 2024.