TVP Reference
PCC 2026 / 017
PR25007
 Maidenhead Custody Build
Multi-Disciplinary Lead Design Services
RIBA Stages 0-3 initially,
Then partnering in RIBA 4-7 from PCSA & build with Main Contractor

Gateway C: Commercial Outcome Report & OPCC Decision Report

Submitted By:
Adrian Woodmore

Date Submitted: 22nd January 2026

# Contract Award (and COR) Sign-Off Sheet

It is the responsibility of the Procurement Department to complete and present this paper to the CGB (this may be by a virtual process)

By approving this document the Commercial Governance Board confirms acceptance of the detail contained within this document, approval to proceed with contract award, implementation and realisation of the benefits.

In the case of a Procurement which results in a new contract (or extension) the document replaces the previous award paper and has a section for the relevant sign-offs below.

Part 1 –
For publication on TVP / PCC Internet Site

Public access to information
The information in this COR is subject to the Freedom of Information Act 2000 (FOIA) and other legislation. Part 1 of this form will be made available on the website within 1 working day of approval. Any facts and advice that should not be automatically available on request should not be included in Part 1 but instead on a separate Part 2 form. Deferment of publication is only applicable where release before that date would compromise the implementation of the decision being approved.

Executive Summary and Recommendations
BACKGROUND / Works identified following the Criminal Justice strategic review, approved by CCMT in April 2021. This specific work was subsequently signed off by Strategic Estate Group (SEG) on 27.07.2023. / Maidenhead police station and custody was originally built in the mid 1970’s as part of a civic development, which also included fire station and magistrate's court. The custody suite was subsequently extended circa 2014. In 2021 the Police and Crime Commissioner approved the purchase of the adjacent court building, consolidating and increasing the available site area. / The facilities, in their current form, do not adequately satisfy operational requirements and fall short of the recommendations of the latest Ministry of Justice guidance. Much of the existing plant and infrastructure is approaching end of life increasing the maintenance burden and disruption to operational business as usual. / The TVP Custody 2030 strategy includes the construction of a new custody suite to replace existing facilities at Maidenhead police station; for which a feasibility study was carried out in 2022 by Corstorphine and Wright. The strategic brief proposes 40nr PACE cells and 6nr enhanced cells; however, it is intended that these numbers are subject to further review and design development to balance operational needs with best value for money; as an initial RIBA 1 task following the appointment of suitable design consultants with Custody design experience. The multi-disciplinary services will cover the core design functions including lead designer, architect, structural and civil, mechanical and electrical, planning, BIM coordination etc. / There will be separate contracts for other services required to complete this project including but not limited to Project Management, Quantity Surveying and Principal Contractor. / Current / Baseline / Budgeted Spend £3,350,000 / Various contract break points will be included at the following stages: / RIBA Stage 0/1 – 2 Feasibility Study and Concept Design, anticipated value £475,000 / RIBA Stage 3 & 4 – Technical Design, anticipated value £1,425,000 / RIBA Stage 5-7 – Construction and Handover £1,450,000 / Subjective Codes: AA130/BLC/295 / Summary of requirement and process: / The tendering process, covered stages MC1 and MC2 of contracting under the NHS Shared Business Services Framework. This process involved two key stages: / MC1 – Selection/Shortlisting: This initial stage focused on evaluating contractors based on key questions regarding their experiences and skills. Four bids were received during this stage, and all four were shortlisted to proceed to the next stage. / MC2 – Tender Evaluation: The bids were evaluated by Procurement and Estates personnel based on three criteria: 40% Cost, 40% Deliverables, and 20% Presentation. The Deliverables was assessed by written submission and moderated to obtain the final score. The presentation was in person and teams, but the scoring methodology was shared amongst all bidders in advance of the meeting without any queries being received. / The costs were spreadsheets shared by procurement with our internal Quantity Surveyor only and segregated from the quality scoring. / Following the completion of this MC2 evaluation process, and presentation to the Capital Projects team, this paper seeks approval to appoint Ryder Architecture Ltd. They achieved the highest overall score in the evaluation, excelling in Cost, Deliverables, and Presentation. A full evaluation summary is provided in Section 2 below. / 1.1.3 Regulation 84 form has been completed and is at Appendix A (Note that by default a regulation 84 form should be completed in all circumstances). This is a record of the exercise required to be kept by the Cabinet Office. / 1.1.4 Contract Terms and Conditions: The suppliers meet all the requirements of the contract terms and conditions and specification and offer the Most Economically Advantageous Solution, as assessed through the evaluation process. / 1.1.5 Legal Implications: This contract has been awarded by a legally compliant methodology / 1.1.6 Equality and Diversity: There are no specific issues with regard to Equality & Diversity with this award. / 1.1.7 Social Value: Unknown at this stage but likely to be limited as this is a highly specialised activity. / 1.1.8 Realisation Implementation Plan. Implementation plan will be discussed and agreed on contract award. / 1.1.9 SF007 Procurement Checklist it up to date and will be finalised and stored upon award contract award / 1.1.10 Contract Management Review: Tier 1 or Tier 2 or Tier 3 / 1.1.11 The procurement process has followed all relevant legislation and complies with the objectives of: Transparency; Delivering value for Money, Maximising Public Benefit, and Acting with integrity and all relevant applicable legislation and regulations / 1.1.12 There is a confidential Part 2 form is for internal use and is not for publication into the public domain due to the sensitive/commercial nature of the information.

# 1.1.12 Attachments
Please include the following attachments as additional supporting information:
 Any additional Supporting information
N/A1.1.13 FINANCIAL IMPLICATIONS - Finance
1.1.13 FINANCIAL IMPLICATIONS / The recommended contract award value is approximately £1,000,000+ less that our original estimate. There is still risk/ contingency allowance within the budget for this and employment of other services. / Due to the procurement process, and our fees estimate being a percentage of total cost, there is still potential variance in overall project costs compared to current budget. The proposal is for the estimated savings at this stage to be retained in contingency for the project budget, while we continue to develop the design and plan for the construction works. / There are contractual break points included within this contract at the end of RIBA 2 and end of RIBA 4. The commitment to end of RIBA 2 for the recommended contract award will be for £1,298,549 which is within the approved budget drawdown for design works to end of RIBA 2, but we will set aside a further provisional sum of £45,000 for potential adjustments for additional design costs which will then be total a cost of £1,343,549 if this additional sum is required.
Is the value of the contract within budget YES	Yes it is within the budget

Comment: The tender sum came in significantly lower than what was originally budgeted for which can go back into contingency.

1.13
ICT IMPLICATIONS
To be completed by the ICT lead this is to include comments about the recommended contract award ICT implications and any risks associated that may lead to additional spend requirements. / ICT requirements to be agreed and worked into the design work being undertaken by this recommended award of multi-disciplinary design team. New ICT technical capabilities \ initiatives will be raised as separate projects as confirmed in CLD.
Add a breakdown of refined ICT resource costings / N/A – see above
State the resource start date for this project.

1.1.13
1.2 RECOMMENDATION / 1.2.1 The Police and Crime Commissioner / Chief Constable of Thames Valley Police (Chief Finance Officer and Director of Finance) are invited to agree the award of contract in respect of the above to Ryder Architecture Ltd. / The above contract is for RIBA Stage 0/1 to 7 over the proposed period of up to 5 years including end of defect liability, with no extension option. Contractual break points included at the end of RIBA 2 and end of RIBA 4. / The total value of this contract is estimated at £1,343,549 over the full project.

Process and COR approval
Role	Name/Job Title/or Shoulder No.	Signature and Sign-Off Date
Project Sponsor (Stakeholder) / Approving the proposal as meeting the requirements	Harvey Golding – C4636 / Yien Hoo	H Golding 27.01.2026 / YE Hoo C7780 27/1/2026
Procurement Business Partner / Approving the award as meeting the commercial and regulatory requirements of the force	A Hughes – C6081	23.01.26
Procurement Lead / Confirming the process as meeting the objectives and regulatory requirements set	Adrian Woodmore
TVP Finance / Confirming that they have approved the budgetary and financial implications of this proposal	Dave Allen	C3572 / 27/01/2026
Legal (If applicable) / Confirming their review of any legal implications of this proposal	N/A

Approval Role	Name or Shoulder Number	Job Title	Signature and Sign-Off Date
Approver / Supporter / approving contract award up to a value of £200,000 and supporting values above £200,000	Richard Fowles	Head of Procurement	28/1/26
Approver / Supporter: / approving contract award up to a value of £1,000,000 and supporting values above £1,000,000	Linda Waters	Director of Finance	31/1/26
Consulted / Approver: / Consulted on contract award values of £200,000 up to £1,000,000 / Approval on contract award values above £1,000,000	Martin Thornley	OPCC - Chief Finance Officer	30/1/26
Approver: / Approval on contract award values above £1,000,000	Gillian Ormston	OPCC - Chief Executive	2/2/26
Final Approver: / Approval on contract award values above £1,000,000	Matthew Barber	Police & Crime Commissioner	3/2/26

Contract Summary and Information for BLPD
Proposed Supplier (s)	Ryder Architecture Limited
Planned Contract Start Date	January 2026 asap
Contract Duration – Initial Term (months)	60 months including defect liability period
Contract Extensions Available (months)	N/A
Contract Value Initial Period (months)	£1,343,549 over the full project.
Contract Value Extension per extensions periods	N/A
Total Contract Value including all extensions	£1,343,549 over the full project.
Collaborative Purchase Information (who are we buying with and what is there proportion of spend).	N/A
ICT resource costs (note not part of contract value)	N/A

Contract Savings (for use on Home Office benefits reporting – NOT TO BE INPUT ON BLPD)
Baseline Spend (highlight any changes to information provided in CLD)	New requirement purchase
Savings Enabled: / Detail at High, Low and Expected level if the savings are likely to be variable e.g. based on demand. / Include Annual & Total Contract Savings	N/A
	N/A
Savings Start Date if different from Contract start date	Cashable:£ / TBC
Collaborative Savings	N/A
Savings Types (based on Savings Definitions in Savings Analysis Worksheet)	Cashable:£ / N/A
Other Benefits:	Implement the Custody Futures strategic programme
Total Savings as a % of baseline spend:	Cashable:£ / N/A